## Summary
Feature Testing Estimation
| Total Numbers | Total Hrs | Man Days
No Of User Stories | 6
Sprint Duration | 10
Efforts for User Story Analysis Test Designing | NA | 12
Efforts for Test Execution | NA | 16
Efforts for Common Activites | NA | 4
Total man days for 6 User Stories
Total Required Resource
Buffer Resources | 0
Total Resources Required | 0
Total Efforts | 0 | 32*6= 192 | 26

## PerUserStory_FT
Per User Story Analysis and Test Planning Activity
Sr. No. | Activities | Sub Activities | Feature Test
|  |  | Efforts (hrs.) | Total Efforts (mins) | Simple | Medium | Complex | Total
1 | Requirement Analysis | Review of User Story and Prototype Document | 1 | 60
|  | Review of High Level System Architecture | 1 | 60
|  | Review of Low Level Design Documents | 1 | 60
2 | Test Planning | Test Strategy Finalization | 1 | 60
|  | Test Plan Creation | 1 | 60
3 | Test Designing | Average test scenarios Designing Per User Story (In Numbers) | 2 | 120 | 4 | 3 | 2 | 9
|  | Review of scenarios | 0.5 | 30
|  | Average Test Case Designing Per User Story (In Numbers) | 2 | 120 | 8 | 6 | 5 | 19
|  | Formal and Peer Review | 0.5 | 30
|  | Update the Test Cases as per Review comments | 0.5 | 30
|  | Import Test Cases to Test Case Management Tool | 0 | 0
|  | Idenfity Smoke and Regression Test Cases | 1 | 60
|  | Create test sessions in Test Case Management Tool for specific environments to be tested | 0.5 | 30
|  | Total Efforts for Analysis | 3
|  | Total Efforts for Test Planning | 2
|  | Total Efforts for Test Designing Activity | 7
|  | Total Hours: | 12
Per User Story Test Execution Activity for One Test Cycle - I
Sr. No. | Activities | Sub Activities | Feature Test
|  |  | Hrs. | Min. | Simple | Medium | Complex
4 | Test Execution | Test Execution for new Feature Test Cases | 2 | 120 | 8 | 6 | 5
|  | Average Time Required to Log and Verify the fixed bugs | 1 | 60
|  | Test Execution for Existing Smoke Test Cases | 2 | 120 |  |  |  | 9
|  | Efforts for Test Execution Activity For One Test Cycle | 5
|  | Number Of Anticipated Cycle | 2
|  | Total Efforts for Execution | 10
Sr. No. | Activities | Sub Activities | Feature Test
|  |  | Hrs. | Min. | Simple | Medium | Complex
5 |  | Test Execution For Existing Regression Test Cases | 2 | 120 |  |  |  | 80
|  | Efforts for Test Execution Activity For One Test Cycle | 2
|  | Number Of Anticipated Cycle | 2
|  | Total Efforts for Execution | 6
Daily Activity/One Time Activity for each User Story
Sr. No. | Activities | Sub Activities | Feature Test
6 | Common Activites | Stand Up Meeting | 1 | 5
|  | Bugs Scrub Meeting | 1 | 5
|  | Discussion with Devlopment Team | 2 | 10
|  | Total Daily Activity | 4
|  | Total Efforts in Hours per User Story ( 12+ 10+6+4) | 32

## Assumptions
Assumption : Efforts are consider per User Story
Sr. No | Assumptions Based On | Simple | Medium | Complex
1 | Calcuation for designing One Scenario (mins) | 10 | 20 | 30
2 | Calcuation for each Test Cases Designing (mins) | 10 | 10 | 10
3 | Calcuation for each Test Case Execution (mins) | 5 | 10 | 15
| One Manday | 8 | Hours